## Project Register
# | 01 · Basic Info | [15 empty] | 02 · Phase, Status & Dates | [8 empty] | 03 · Progress & Financial | [9 empty] | 05 · Contract & Financial Security | [16 empty] | 06 · GeoTagging | 07 · Action & Remarks |  |  | 08 · O&M Details (Completed projects)
# | Project Name | Sector | Scheme(s) | City | Division | Region | Contractor | PD | Scheme / Category | Main Work | Physical Work Progress | Contract Type | Sponsoring Department | Implementing Agency | Project Sanction Date | Project Brief | Project Stage | Execution Status | Status (auto) | Pre-Monsoon Critical | Planned End Date | Revised End Date | Delay Days (auto, simplified) | Delay Reason / Root Cause | Department / Agency Stuck At | Physical Progress % (Actual) | Physical Progress % (Scheduled) | Financial Progress % | Total CoS Count (auto) | Total EoT Days (auto) | AA Amount (Rs. Cr.) | Revised AA Amount (Rs. Cr.) | Sanctioned Cost (Rs. Cr., auto) | Agreement Amount (Rs. Cr.) | Financial Progress (Rs. Cr.) | Agreement Number | Agreement Date | Appointed Date | Contract Value (Rs. Cr.) | Mobilization Advance (Rs. Cr.) | Mob. Advance Recovered (Rs. Cr.) | PBG Number | PBG Amount (Rs. Cr.) | PBG Expiry Date | PBG Issuing Bank | EMD Amount (Rs. Cr.) | EMD Reference Number | EMD Date | Total Payments Made (Rs. Cr.) | Last Payment Date | Last RA Bill No. | Retention Money Held (Rs. Cr.) | Geo-Tagging URL (overview link) | Priority | Outstanding Gap? | Gap / Remark | O&M Applicable | O&M Start Date | Total O&M Period (Months) | O&M End Date (auto, override-able) | O&M Agency / Contractor | O&M Status (Manual Override) | O&M Remarks
| Text | Dropdown: Sector | Text | Text | Dropdown: Division | Auto (formula) | Text | Text | Auto (formula) | Text | Text | Dropdown: ContractType | Text | Text | Date | Text (long) | Dropdown: ProjectStage | Dropdown: ExecStatusCode | Auto (formula) | Dropdown: YesNo | Date | Date | Auto (formula) | Text | Text | Number | Number | Number | Auto (formula) | Auto (formula) | Number | Number | Auto (formula) | Number | Number | Text | Date | Date | Number | Number | Number | Text | Number | Date | Text | Number | Text | Date | Number | Date | Text | Number | Text | Dropdown: Priority | Dropdown: YesNo | Text (long) | Dropdown: YesNo | Date | Number | Auto (formula) | Text | Dropdown: OMStatus | Text (long)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
Formulas:
Delay Days (auto, simplified) = IF(OR([Planned End Date]="",[Execution Status]="COMPLETED"),0,MAX(0,TODAY()-[Planned End Date]))
O&M End Date (auto, override-able) = IF(AND([O&M Start Date]<>"",[Total O&M Period (Months)]<>""),EDATE([O&M Start Date],[Total O&M Period (Months)]),"")

## GeoTagging Photos Log
Project Name | Photo URL / Link | Caption | Date Added

## CoS-EoT Log
Project Name | CoS Number | CoS Date | Category | CoS Amount (Rs. Cr.) | Variation % | EoT Number | EoT Days Granted | Time Linked? | Original End Date | New End Date (After EoT) | Revised Date (if Different)

## Management Actions Log
Project Name | Topic | Status | Deadline Date

## Lists
Sector | Division | ContractType | ProjectStage | ExecStatusCode | ExecStatusLabel | YesNo | Priority | OMStatus | CoSCategory | MgmtStatus | Scheme | Division | Region
Crematorium | Arwal | Works Contract | Conceptualization | NOT_STARTED | Not Started | Yes | High | Not Started | SCOPE ADDITION | Open | Namami Gange | Arwal | South Bihar
Sewerage | Aurangabad | Service Contract | Design | IN_PROGRESS | In Progress | No | Medium | Ongoing | SCOPE DELETION | Closed | AMRUT 1.0 | Aurangabad | South Bihar
SWD | Banka | O&M Contract | Pre-Tender | DELAYED | Delayed |  | Low | Expiring Soon | DESIGN CHANGE |  | AMRUT 2.0 | Banka | South Bihar
Water Supply | Bhagalpur | Others | Tender | ON_HOLD | On Hold |  | N/A | Expired | QUANTITY VARIATION |  | SAAT NISHCHAY | Bhagalpur | South Bihar
Others | Bhojpur |  | Construction | COMPLETED | Completed |  |  | Handed Over to ULB | OTHERS |  | STATE FUNDED | Bhojpur | South Bihar
| Buxar |  | O&M | [7 empty] | Pragati Yatra | Buxar | South Bihar
| Gayaji |  | Completed | [7 empty] | Patna Smart City | Gayaji | South Bihar
| Jamui | [9 empty] | MMSSVY | Jamui | South Bihar
| Jehanabad | [10 empty] | Jehanabad | South Bihar
| Kaimur | [10 empty] | Kaimur | South Bihar
| Lakhisarai | [10 empty] | Lakhisarai | South Bihar
| Munger | [10 empty] | Munger | South Bihar
| Nalanda | [10 empty] | Nalanda | South Bihar
| Nawada | [10 empty] | Nawada | South Bihar
| Patna Azimabad | [10 empty] | Patna Azimabad | South Bihar
| Patna Bankipur | [10 empty] | Patna Bankipur | South Bihar
| Patna Kankarbagh | [10 empty] | Patna Kankarbagh | South Bihar
| Patna Nutan | [10 empty] | Patna Nutan | South Bihar
| Patna West | [10 empty] | Patna West | South Bihar
| Patna Patliputra | [10 empty] | Patna Patliputra | South Bihar
| Patna East | [10 empty] | Patna East | South Bihar
| Patna City | [10 empty] | Patna City | South Bihar
| Rohtas | [10 empty] | Rohtas | South Bihar
| Sheikhpura | [10 empty] | Sheikhpura | South Bihar
| Araria | [10 empty] | Araria | North Bihar
| Begusarai | [10 empty] | Begusarai | North Bihar
| Darbhanga | [10 empty] | Darbhanga | North Bihar
| Gopalganj | [10 empty] | Gopalganj | North Bihar
| Katihar | [10 empty] | Katihar | North Bihar
| Khagaria | [10 empty] | Khagaria | North Bihar
| Kishanganj | [10 empty] | Kishanganj | North Bihar
| Madhepura | [10 empty] | Madhepura | North Bihar
| Madhubani | [10 empty] | Madhubani | North Bihar
| Muzaffarpur | [10 empty] | Muzaffarpur | North Bihar
| West Champaran (Betiah) | [10 empty] | West Champaran (Betiah) | North Bihar
| East Champaran | [10 empty] | East Champaran | North Bihar
| Purnea | [10 empty] | Purnea | North Bihar
| Saharsha | [10 empty] | Saharsha | North Bihar
| Samastipur | [10 empty] | Samastipur | North Bihar
| Saran | [10 empty] | Saran | North Bihar
| Sheohar | [10 empty] | Sheohar | North Bihar
| Sitamarahi | [10 empty] | Sitamarahi | North Bihar
| Siwaan | [10 empty] | Siwaan | North Bihar
| Supaul | [10 empty] | Supaul | North Bihar
| Vaishali | [10 empty] | Vaishali | North Bihar